Scope of Work

Project 4: National Risk Index Analysis and Bias Evaluation

Team Members: Anthony Perrotto, Collin Mangnall, Dawa Lamu Tamang, Zane Smith

CIVE 202 – Civil Engineering Analysis II

Client: Risk Averse, LLC

Date Submitted: April 21, 2026

# Project Summary

Natural disasters pose significant risks to communities across the United States, impacting infrastructure, economies, and vulnerable populations. To assess these risks, the Federal Emergency Management Agency (FEMA) developed the National Risk Index (NRI), which evaluates risk using Expected Annual Loss, Social Vulnerability, and Community Resilience.

The purpose of this project is to analyze NRI data at the Census Tract level for Texas and Colorado and evaluate whether FEMA’s risk methodology introduces bias against socially vulnerable communities. Specific hazards examined include lightning and winter weather in Colorado, and heat waves and tornadoes in Texas. In addition, this project will develop an alternative risk model that places greater emphasis on social vulnerability and compare it with the existing NRI framework using the following formula:

Risk Score = (Expected Annual Loss × 0.40) + (Social Vulnerability × 0.45) + ((1 − Community Resilience) × 0.15)

The results will provide insight into how risk is distributed across communities and how different definitions of risk may influence decision making and resource allocation.

# Project Goals

The goal of this project is to analyze and evaluate natural disaster risk using publicly available NRI data and assess potential bias in FEMA’s methodology. The client has requested the following analyses:

- Analyze risk at the Census Tract level for any two states, Texas and Colorado, focusing on lightning and winter weather in Colorado and heat waves and tornadoes in Texas.

- Explain how FEMA defines and calculates risk using Expected Annual Loss, Social Vulnerability, and Community Resilience.

- Develop an alternative risk formula that places greater emphasis on social vulnerability and compare it with FEMA’s model at the county level for each selected hazard.

- Identify potential bias in risk classification and discuss its implications for affected communities.

# External Resources

These resources will be used to obtain datasets and supporting documentation for the risk analysis and model development:

- FEMA National Risk Index Data:  https://hazards.fema.gov/nri/data-resources

- ATSDR Social Vulnerability Index: https://www.atsdr.cdc.gov/place-health/php/svi/svi-data-documentation-download.html

# Project Tasks

Our team will complete the following tasks:

## Task 1: Data Acquisition and Preparation

Our team will download the National Risk Index (NRI) Census Tract dataset from the FEMA data resources website, along with the NRI Data Dictionary and Hazard Information files. The CDC Social Vulnerability Index (SVI) dataset will also be obtained. All datasets will be reviewed in Python to confirm they are properly structured for analysis. Data cleaning will include filtering records for Texas and Colorado, replacing FEMA’s placeholder missing value code (−9999) with null values using the numpy library, and selecting relevant variables such as Expected Annual Loss (EAL), Social Vulnerability Score, Community Resilience Score, and NRI Risk Scores. The NRI and SVI datasets will then be merged on the shared geographic identifier STCOFIPS using the pd.merge() function in the pandas library. As a final deliverable, our team will provide both the raw and cleaned data files.

## Task 2: Understanding and explaining the NRI Model

Our team will review FEMA documentation to understand how the NRI defines and calculates risk. This includes analyzing how hazard exposure, Expected Annual Loss, Social Vulnerability, and Community Resilience are combined into a composite risk score. This understanding will be used to clearly explain the NRI methodology in the final project report.

## Task 3: Data Analysis and Summary Statistics

Using Python with the pandas and numpy libraries, our team will analyze the NRI dataset for both Texas and Colorado. Summary statistics including mean, median, minimum, and maximum values will be calculated for key variables such as Expected Annual Loss, Social Vulnerability, Community Resilience, and NRI Risk Scores for each selected hazard. This analysis will help identify trends and differences in risk distribution across the two states.

## Task 4: Development of Alternative Risk Model

Our team will develop an alternative risk formula designed to reduce bias in FEMA’s methodology by increasing the weight assigned to social vulnerability. The NRI and SVI datasets will be merged on the STCOFIPS geographic identifier to enable tract-level analysis. The alternative risk score will then be calculated for each selected hazard in both states by creating new columns in the merged dataset using the pandas library. The formula applies weights of 0.40 to Expected Annual Loss, 0.45 to Social Vulnerability, and 0.15 to the inverse of Community Resilience, reflecting a greater emphasis on the social dimensions of risk.

## Task 5: Sensitivity Analysis and Comparison

Our team will perform a sensitivity analysis by comparing FEMA’s NRI risk scores with the alternative model scores for each selected hazard and state. Using the groupby() and agg() functions in pandas, county-level mean scores will be computed for both models and compared side by side. Records with missing values will be excluded from calculations to ensure result’s accuracy. Differences in county-level rankings will be examined to evaluate how the change in weighting affects risk classification.

## Task 6: Visualization and Mapping

Using Python with the matplotlib and GeoPandas libraries, our team will create graphical visualizations and choropleth maps for each state. Dual-axis bar charts will be produced for each hazard, displaying county level NRI scores alongside alternative model scores to allow direct comparison. Choropleth maps will be generated at the Census Tract level using the NRI shapefile data, displaying both the original NRI risk scores and the alternative risk scores for Colorado and Texas. All maps will be reprojected to the U.S. national equal-area projection (ESRI:102003) for accurate geographic display.

## Task 7: Documentation and Reporting

Our team will prepare a complete set of documentation, including an annotated Python code document explaining each function and its purpose, a written report summarizing the analysis findings, and a GitHub repository containing all project materials organized by deliverable type. The report will include a discussion of bias in FEMA’s risk classification, the ethical implications of different risk definitions, and the impact of those definitions on socially vulnerable communities.

# Project Deliverables

The deliverables requested by the client, Risk Averse, LLC, are summarized in the following table:

| Deliverable | Description | Due Date |
| --- | --- | --- |
| Scope of Work | Project plan outlining goals, tasks, and methods | 04/21/2026 |
| Raw Data Files | Original NRI and SVI datasets | 04/21/2026 |
| Cleaned Data Files | Processed and merged datasets used in analysis | 04/21/2026 |
| Python Code | Jupyter Notebook containing all project code | 04/21/2026 |
| Annotated Code Document | Explanation of code functions and steps | 04/21/2026 |
| Gantt Chart | Timeline of project tasks | 04/21/2026 |
| Timesheet | Record of team contributions | 04/21/2026 |
| Final Report | Summary of analysis, results, and conclusions | 04/21/2026 |
| GitHub Repository | Organized project files and documentation | 04/21/2026 |